## Estimation Formate
		Technology
		Department
		Project Name

Sno.	Task	Description		Comment/Queries	Days/Hours
	General site Module - 1

1	Design	Create the Design for site and Approval from Client		Design suggetion from the client	3 Days after Design Approve
2	Create the HTML from the Mockup	This is part of Design in we will create the HTML to implement on site			2 Days
3	Configuration of Site	Configure the site on our demo server			1 Day
4	Registration of User's	we will provide the user's registration with Facebook and Google Plus		If wants to have registration with another social site	2 Days
5	Making the Basic informal site for general user	This is the view of site that for general user without registration on site		Client will provide the content for all informal pages like about US and feaures etc	3 Days

User Module - 2

6	Register User Profile	User can see the Detail after the login and can edit the his profile			1 Day
7	User DeshBoard	In this section user can see the content of logged In user And about the subject and How much test He given , test score etc.			2 Days
8	Follows the Other user	Here Logged in User can follow other user and ask question and have conversation			1 Day

Group Study Module - 3

9	Create the Group	Creating the group When User is paid User and Invite for Be in the Group.			2 Days
10	Conversation	IN the Group All user can have conbined conversation and Discuss the problem related to Study			2 Days

Subject Module - 4

11	Create the Test for the student	Admin will create the Tests like IIT and etc.			1 Day
12	Include the subjects in the Tests	Here Admin will create the subjects for the tests			1 Day
13	Create the Chapter's in the subject	Creating the different Chapter for Various Branch of subject			1 Day
14	Assign the Topic in the chapter's	Every Chapter will have the Different Topic for study			2 Days
15	Study Material	Add study material for each and every Topic Like Video, PDF files, PPT's etc			2 Days
16	Add the Practice Question for Every Topic	Before the test Student can do pratice on the question.			1 Day
17	Basic Concept	Adding the Concept for all the Topic for making the Study Easy			1 Day
18	LeadBoard	IN this Student can see the His result according to assignment and test results			2 Days

Test Modules - 5
19	Creating the Test series	Admin will Create the test series for the Different Topic			2 Days
20	Level's of Test	Create the different level's of Test So student can select the Test level And Admin will add the question for that level			3 Days
21	Statistic of Test score	Here user and admin can see the student score level for the Future preparation			1 Day
22	Comparesion between the Student Answere and Correct Answere	We will Provide the Comparision of Answere for student so He can know the Actual Difference			2 Days
23	Previos Year Test	Admin will add the Previous Year Paper's			2 Days

Subscription Module - 6

24	Add the different Subscription for the student	Admin will add the Different types of subcription for the student so He can choose			2 Days
25	Payment Integration	We can use the Different Payment API for payment Like PayU, CCAvanue etc		Client need to purchase the Payment API	2 Days

Social Module - 7

26	Create the Blogs	We will create Blogs So Student or Teacher can put there Topic to discuss			3 Days
27	Create Bytes	Provide the Plateform for Student So they can get the Information about the different type of Exams			3 Days
28	Discuss	Plateform for discuss for all Student and student			2 Days

Job Module - 8

29	Making the Job posting for the Different post	Admin will post the Jobs accaording to category like teacher, Developer etc			2 Days

				Testing and Deployement	6 Days
				Total Days	60 Days

	*These are all working Days. Its not Included any Festival or Other office vacation
	*You will get Daily Update reports for the Work progress. And after Freez the requirement If Any changes will be paid changes.
	*Suggestion's are Invited

	Nubmer of Developer	1
	Number of Designer	1
	Team Lead
	Project Manager
	Accounts Manager

	Note: / 1) Estiamtion is done as per our understading and the details provided by client. / 2) It may vary if requirement changes or change request. / 3) Consider working hours or days.

	Working Schedule: / 1) Monday to Friday 11.00 am to 8.00 PM IST / 2) Saturday 11.00 am to 3 PM IST / 3) 180 working hours per month